nORTHUMBERLAND SCHOOLS’ ATHLETIC ASSOCIATION

SCHOOL TEAM CROSS CHAMPIONSHIPS 2015

Event Plan

Contents

Introduction	  1

Event Description

General Information

Site Description

Course Details

Management Structure	2

Key Personnel

Set up / Dismantle	3

Roles & Responsibilities	4

Communications	5

Marshalls	6

Lost Children	7

Emergency Management	8

Severe Weather 	9

Timetable	10

- Introduction

Event Description

The Northumberland Schools’ Athletic Association, are to hold the School Team Cross Country Championships at Gateshead Stadium with the help and support of Gateshead College and the North East Counties Athletics Association Officials.

# General Information

The Races will take place on Tuesday 4th October 2016

Setup will start at 9:30am, and Dismantle of the course should be finished by 4:00pm with the first of ten races starting at 1:00 pm. Plan of the course enclosed.

Around 600 athletes aged between 8 – 11 will be taking part and will have been selected to participate by their schools. This event is preceded by the Cross Country Cup, Round 1, for Juniors (Y7/Y8) and Inters (Y9/Y10).

Site Description

The course will be held on an established cross country course within Gateshead Stadium Grounds, located to the SE area beyond the athletics arena, previously known as the ‘Gateshead Bowl’.

Course Details

GRASS with 2 small hills / approximate start times

Y3 Girls:  Start- 1.00pm / Distance 985 metres

Y3 Boys: Start- 1.10pm / Distance 985 metres

Y4 Girls:  Start- 1.20pm / Distance 985 metres

Y4 Boys: Start- 1.30pm / Distance 985 metres

Y5 Girls:  Start- 1.40pm / Distance 1555 metres

Y5 Boys: Start- 1.50pm / Distance 1555 metres

Y6 Girls:  Start- 2.00pm / Distance 1555 metres

Y6 Boys: Start- 2.10pm / Distance 1555 metres

- Management Structure

The Northumberland Schools’ Athletic Association Executive Committee are         responsible for the organisation of this event. Below the Executive Committee we have a Cross Country Organiser (Paul Ponton), Course Administrator (Kevin Flannery) and Helen Buist & Ken Wilkinson at Race HQ/Results.

Key Personnel

| Organisation | Name | Role | Contact Number |
| --- | --- | --- | --- |
| NSAA | Kevin Flannery Course Administrator | Course setup / Dismantle Brief Marshall’s | 07443 453169 Radio |
| GC | Staff | Provision of indoor toilets |  |
| NSAA | Paul Ponton Event Organiser | Sports Hall set up Start / Finish Area | 07747 791 732 Radio |
| NSAA | Helen Buist Ken Wilkinson | Race HQ / Results |  |
| NECAA NECAA NECAA NECAA NECAA NECAA NSAA NECAA NECAA NECAA NSAA NECAA NECAA | George Patterson +SW Nick Hodgson Ian Schofield Tom Morgan Linda Schofield Keith Willshire Bill Parker + Pete Ken Wilkinson Richard Balding Les Venmore Jim Scott + Dave K Ralph Dickenson Mick Frazer Margaret Watson | Starter Race Referee / Finish Marshall A Marshall B Marshall E Marshall F Marshall G Marshall H Timekeeper Timekeeper Timekeeper Finish Finish Finish | With Steve Walker Radio Radio Radio Radio Radio 07821 807016 |

3. Set up / Dismantle

3.1 The course setup will start at 9:30am using marker posts, marker tape and signage

3.2 Start and Finish areas to be established and if weather conditions allows, will be highlighted with marker tape.

3.3 STC Events staff will help with the erection and set up PA system. To be agreed

3.4 Maps of the course to be displayed

3.5 Check course prior to first race starting, with Marshalls in position

3.6 Dismantle of the course after last race has finished

3.7 Male, female and disabled toilets are situated in the College Building.

4. Roles and Responsibilities

4.1 Event Organiser – Paul Ponton

In the event of an emergency situation this person is responsible for emergency announcements to all staff present.

He will have overall responsibility for the safe operation of the event.

4.2 Role of Northumbria Police

It is not intended for Northumbria Police to be on site.

In the event of an emergency situation their point of contact will be the Paul Ponton

4.3 Role of First Aid

Teachers are responsible for their own teams. NSAA will provide a medical kit and a qualified Paediatric first aider.

4.4 Role of Tyne and Wear Fire Brigade

It is not anticipated that Tyne and Wear Fire Brigade will have a presence on site

5. Communication

Key Marshalls working on the course will be issued with radios.

The Event Organiser (Paul Ponton) and the Course Administrator (Kevin Flannery) will have mobile telephones. Paul and Kevin will also have a Radio.

All other staff will be working within close proximity to each other and therefore will not be using any two way radio communication systems.

6. Marshalls

Marshall  A  ~  Located at position A on site plan (This Steward will

Direct runners in the right direction, Inform event co-ordinator of any injured runners and provide space blanket if needed

Marshall  B  ~  Located at position B on site plan (This Steward will

Direct runners in the right direction, and provide space blanket if needed).

Marshall  E  ~  Located at position E on site plan (This Steward will

Direct runners in the right direction, Inform event co-ordinator of any injured runners and provide space blanket if needed)

Marshall  F  ~  Located at position F on site plan (This Steward will

Direct runners in the right direction, Inform event co-ordinator of any injured runners and provide space blanket if needed), and will have First Aid Kit if needed.

Marshall  G ~  Located at position G on site plan (This Steward will

Direct runners in the right direction, Inform event co-ordinator of any injured runners and provide space blanket if needed)

Marshall  H ~  Located at position H on site plan (This Steward will

Direct  runners in the right direction).

All Marshalls will wear high visibility vests/coats and A, E, F and G will have Radios.

All Marshalls will be given instructions prior to taken up position.

7. Lost Children

Due to the size and nature of this event there is no dedicated lost children area. Any staff finding a child should report to the Leisure Centre where the Staff will follow the Council procedures.

8. Emergency Management Procedures

8.1 Risk Assessment

Risk assessments of all activities have been carried out. They have identified sources of potential problems and designed solutions to ensure that such dangers are to be eliminated prior to the event or reduced to a manageable level that would allow the event to proceed safely.

8.2 Emergency Situations

An Emergency Situation is described as ‘An occurrence that poses a threat of serious injury, loss of life or a breakdown in public order and does require the Police to assume the co-ordination of its resolution’.

Whilst the Event Organiser is responsible for dealing with untoward incidents surrounding the event, those involved must be aware of their own ability to cope and recognise the occurrence of Emergency Situations. In such circumstances responsibility for co-ordination of the response will pass to the police. During an emergency situation it is essential that all staff consult with the Police and seek their advice.

8.3 Emergency Response Plan

In the event of a situation arising, the following plan should be implemented:

- Any member of staff becoming aware of a potential incident /situation must advise the Event Organiser located at the Start / Finish area, as soon as possible. If unable to contact the event co-ordinator advise Race HQ in the Leisure Centre Sports Hall.

- On receipt of this information the event organiser will conduct an assessment to determine if the circumstances do, in fact amount to a potential emergency situation. If assessed as such the emergency plan will be implemented.

- The Event Organiser will stop any activities. An announcement made following the lines of  “ Could we please ask that you be patient, there will be a short delay in the programme”

- The Event Organiser will liaise with the relevant emergency services and determine the appropriate course of action. This will then be relayed to all staff and should act as per their issued instructions.

- The Events Organiser will then make a public announcement giving an appropriate message in a clear and concise manner.

- If an evacuation is required, the event will not re-start. The Event Organiser must account for all staff once emergency services have taken control.

9. Severe Weather Conditions

In the event of severe weather conditions the Event Organiser will decide if it is safe to hold the event. Should conditions dictate that it is not safe to hold the event it will either be cancelled or postponed.

10.Timetable / Schedule

| Time/Date | Duty/Activity | Staff |
| --- | --- | --- |
| 9:30am | Deliver marker posts, tape to Gateshead Stadium | Kevin F |
|  | Deliver PA , to Gateshead Stadium | Events Team |
| 9:30am 9:00am | Setup course, display course details Establish Registration / results Area on Start/Finish field. | Kevin F Helen B Paul P Ken W |
| 11:00am 11.30am 12:30pm | Establish First Aid Area Pupils arrive on site to walk the course Brief Marshall’s and other helpers | Paul P Kevin F |
| 12:50pm | Officials / Marshall’s in place |  |
| 1:00pm | Commence First Race | Bill McGuirk |
| 2:45pm | Approx finish of last race |  |
| 2:45pm | Dismantle Course, other Equipment | Kevin F Ken W Events Team |
| 3.30pm | Leave Site |  |